## Instructions
Webinar Program Risk Assessment
Instructions
Use this tool to document webinar program risks, assess their impact & probability, and to develop risk mitigation plans.
1. In the "Webinar Program Risk Assessment" tab at the bottom of this spreadsheet, conduct your risk assessment.
2. Enter a description for the event that could put your project or company at risk.
3. Consider the expected outcome resulting from this risk and enter into the appropriate column.
4. Assess the level of impact resulting from this risk being realized (select from drop-down list: High, Medium, Low).
5. Determine the probability of this risk occuring (select from drop-down list: High, Medium, Low).
6. Develop a risk mitigation plan for each risk and prioritize efforts based on level of impact and probability of occurrence.

## Webinar Program Risk Assessment
Webinar Program Risk Assessment
Risk | Event Description | Expected Outcome | Impact | Probability | Risk Mitigation Plan
1 | Incomplete Webinar Program Strategy | Webinar program will fail | HIGH | HIGH | Use the Webinar Program Methodology to help establish a clear webinar strategy
2 | Lack of Buy-In from Senior Executives | Insufficient funding | HIGH | MED | Build a Business Case and outline a Project Plan to obtain buy-in
3 | Technical Difficulties | End-user frustration | HIGH | LOW | Communicate technical difficulties openly & have a continuity plan in place
4 | Insufficient Resources | Employee backlash due to workload | HIGH | HIGH | Use Business Case to justify new hires and use our job descriptions for roles
5 | Selecting the Wrong Promotional Channels | Poor attendance | LOW | MED | Use the Webinar Promotions Plan Template to document promotions in advance
6 | Incorrectly Measuring Webinar Metrics | Difficulty in demonstrating ROI | HIGH | MED | Use the Webinar Metrics Dashboard and Objectives Scorecard
7 | Inconsistent Brand Messaging | Loss of business reputation | HIGH | MED | Ensure consistent look & feel for all selected channels and adhere to graphics policies
8 | Negative Feedback Posted by Attendees | Impact on sales and bottom line | MED | MED | Monitor channels pro-actively and have resources in place to discuss complaints
9 | Lack of Participation by Attendees | Goals will not be reached | LOW | HIGH | Stimulate conversation through various channels and offer value-add content
10 | Bandwidth Issues | Downtime due to excessive usage | MED | LOW | Ensure IT has allocated the appropriate amount of bandwidth
11 | Enter Other Events Below